## Sheet1
To Do List
thing | section | urgency | done?
get icon for replay | maps | high | done
add skylers replay fucntion | maps | high | done
update india map data | maps | middle | done
apply map/chart titles | body | high | done | Emily
apply copy edits | body | high | done | Emily
Update Mapbox design | maps | medium | done
update title | body | high | done?? | Emily
update subtitle | body | high | done?? | Emily
apply map/chart titles | body | high | done
follow buddy bubble | body | middle | done
remove extra charts | charts | high | done
update footer style | body | high | done | Talk to team about this
update footer credits | body | high | done | Talk to team about this
change colors of pull quotes | body | high | done
regigger the top chart | charts | high | done
regigger the bottom chart | charts | high
order of data incorrect for a few charts | charts | high
update footer notes | body | high |  | Kristin
update report links | body | high
update button links | body | high
update github link | body | high
apply copy edits | body | high
make charts load better on mobile | charts | high
update social media buttons | body | high |  | talk to team
full responsive on load | all | high
fix scale on ward distros | charts | high
build appendix button | body | high
fade in maps on full load | maps | middle
india bubble stroke | maps | middle
sky bubble stroke | maps | middle
India and skyler name on map | maps | middle
Lato to map? | map | low
Add in extra source info for ward | body | medium
full responsive on drag | all | medium
add bubble to distro chart | charts | low
white stroke to ward maps | maps | medium
make dots darker in maps? | maps | medium |  | Ask Mal????
note that this is a proportion in ward map | maps | medium
chart margins | charts | medium
remove ticks from axis | charts | low
firefox PC | QA | high
chrome PC | QA | high
IE PC | QA | high
safari Mac | QA | high
phone | QA | high
add publication date to top of page, remove copyright date from footer | QA | high
remove fonts where need not be | QA | high
remove mobile listeners | QA | high
remove js libraries | QA | high
libraries to remove | remove?
Allwardsdistro | jquery?
india map | jquery?
skyler map | jquery?